## Sheet1
Key | Summary | Status | Issue Type | Priority | Created | Updated | Due Date | Assignee | Reporter | Link | Update_Due_Date | Meeting_Comments | Age_Days | Has_Due_Date | Lag_Days | Due_Deviation_Bucket
CR-1001 | Update TLS certificates for prod cluster (variant 1) | In Progress | Change Request | High | 2025-06-05 16:15 | 2025-10-23 16:15 | 2025-09-14 | Alice Martin | Paul Davis | https://jira.example.com/browse/CR-1001 |  |  | 331 | TRUE | 231 | 230
CR-1002 | Migrate database to PostgreSQL 16 (variant 2) | In Progress | Change Request | High | 2026-03-15 16:15 | 2026-03-16 16:15 | 2026-03-26 | Eve Santos | James Taylor | https://jira.example.com/browse/CR-1002 |  |  | 48 | TRUE | 38 | 35
CR-1003 | Implement rate limiting on public API (variant 3) | In Progress | Change Request | Medium | 2025-07-15 16:15 | 2026-04-20 16:15 | 2025-10-13 | Charlie Kumar | James Taylor | https://jira.example.com/browse/CR-1003 |  |  | 291 | TRUE | 202 | 200
CR-1004 | Refactor payment gateway integration (variant 4) | In Progress | Change Request | Low | 2026-02-06 16:15 | 2026-03-13 16:15 | 2026-03-28 | Charlie Kumar | James Taylor | https://jira.example.com/browse/CR-1004 |  |  | 85 | TRUE | 36 | 35
CR-1005 | Consolidate microservice configs to Vault (variant 5) | Under Review | Change Request | Low | 2026-03-12 16:15 | 2026-04-03 16:15 | 2026-05-03 | Frank Muller | Olivia Brown | https://jira.example.com/browse/CR-1005 |  |  | 51 | TRUE | 0 | 0
CR-1006 | Upgrade Kubernetes to v1.29 (variant 6) | Under Review | Change Request | Low | 2025-07-28 16:15 | 2025-09-06 16:15 | 2025-09-21 | Eve Santos | Nate Williams | https://jira.example.com/browse/CR-1006 |  |  | 278 | TRUE | 224 | 220
CR-1007 | Enable SSO for internal admin portal (variant 7) | In Progress | Change Request | Medium | 2025-07-07 16:15 | 2025-07-30 16:15 | 2025-07-22 | Alice Martin | Maria Lopez | https://jira.example.com/browse/CR-1007 |  |  | 299 | TRUE | 285 | 285
CR-1008 | Patch CVE-2025-1234 in auth library (variant 8) | Under Review | Change Request | High | 2026-03-08 16:15 | 2026-04-17 16:15 | 2026-05-12 | Charlie Kumar | Maria Lopez | https://jira.example.com/browse/CR-1008 |  |  | 55 | TRUE | -9 | -10
CR-1009 | Migrate database to PostgreSQL 16 (variant 9) | Closed | Change Request | Medium | 2025-05-20 16:15 | 2026-04-16 16:15 | 2025-08-22 | Eve Santos | Maria Lopez | https://jira.example.com/browse/CR-1009 |  |  | 347 | TRUE | 254 | 250
CR-1010 | Decommission legacy monolith service (variant 10) | Closed | Change Request | High | 2026-02-04 16:15 | 2026-04-26 16:15 | 2026-03-17 | Charlie Kumar | James Taylor | https://jira.example.com/browse/CR-1010 |  |  | 87 | TRUE | 47 | 45
CR-1011 | Add multi-region failover support (variant 11) | Approved | Change Request | High | 2026-01-01 16:15 | 2026-04-14 16:15 |  | Bob Chen | Paul Davis | https://jira.example.com/browse/CR-1011 |  |  | 121 | FALSE
CR-1012 | Introduce feature flag system (variant 12) | Rejected | Change Request | Medium | 2025-11-18 16:15 | 2026-02-27 16:15 | 2026-01-27 | Charlie Kumar | Maria Lopez | https://jira.example.com/browse/CR-1012 |  |  | 165 | TRUE | 96 | 95
CR-1013 | Decommission legacy monolith service (variant 13) | Closed | Change Request | Medium | 2025-12-23 16:15 | 2026-02-28 16:15 |  | Eve Santos | Olivia Brown | https://jira.example.com/browse/CR-1013 |  |  | 130 | FALSE
CR-1014 | Migrate CI/CD pipeline to GitHub Actions (variant 14) | Open | Change Request | Medium | 2025-10-25 16:15 | 2026-03-04 16:15 | 2025-11-18 | Grace Kim | James Taylor | https://jira.example.com/browse/CR-1014 |  |  | 189 | TRUE | 166 | 165
CR-1015 | Consolidate microservice configs to Vault (variant 15) | Open | Change Request | Medium | 2026-02-09 16:15 | 2026-04-04 16:15 | 2026-05-28 | Eve Santos | Olivia Brown | https://jira.example.com/browse/CR-1015 |  |  | 82 | TRUE | -25 | -25
CR-1016 | Enable SSO for internal admin portal (variant 16) | Rejected | Change Request | High | 2025-08-01 16:15 | 2025-08-06 16:15 | 2025-10-17 | Eve Santos | Nate Williams | https://jira.example.com/browse/CR-1016 |  |  | 274 | TRUE | 198 | 195
CR-1017 | Refactor payment gateway integration (variant 17) | Approved | Change Request | Critical | 2025-06-04 16:15 | 2026-01-12 16:15 | 2025-07-18 | Frank Muller | Nate Williams | https://jira.example.com/browse/CR-1017 |  |  | 332 | TRUE | 289 | 285
CR-1018 | Introduce feature flag system (variant 18) | Open | Change Request | Low | 2025-08-15 16:15 | 2026-05-01 16:15 |  | Charlie Kumar | Paul Davis | https://jira.example.com/browse/CR-1018 |  |  | 260 | FALSE
CR-1019 | Upgrade Kubernetes to v1.29 (variant 19) | Closed | Change Request | Low | 2025-06-21 16:15 | 2025-09-11 16:15 | 2025-08-14 | Eve Santos | Nate Williams | https://jira.example.com/browse/CR-1019 |  |  | 315 | TRUE | 262 | 260
CR-1020 | Update TLS certificates for prod cluster (variant 20) | Open | Change Request | High | 2025-08-21 16:15 | 2026-01-25 16:15 | 2025-10-13 | Eve Santos | James Taylor | https://jira.example.com/browse/CR-1020 |  |  | 254 | TRUE | 202 | 200
CR-1021 | Add OpenTelemetry tracing to order service (variant 21) | Closed | Change Request | Medium | 2026-03-16 16:15 | 2026-03-20 16:15 |  | Bob Chen | Olivia Brown | https://jira.example.com/browse/CR-1021 |  |  | 47 | FALSE
CR-1022 | Update TLS certificates for prod cluster (variant 22) | Closed | Change Request | Medium | 2025-07-21 16:15 | 2026-02-22 16:15 | 2025-10-03 | Frank Muller | Maria Lopez | https://jira.example.com/browse/CR-1022 |  |  | 285 | TRUE | 212 | 210
CR-1023 | Migrate CI/CD pipeline to GitHub Actions (variant 23) | Closed | Change Request | Medium | 2025-11-20 16:15 | 2026-02-23 16:15 | 2026-02-20 | Bob Chen | Maria Lopez | https://jira.example.com/browse/CR-1023 |  |  | 163 | TRUE | 72 | 70
CR-1024 | Update TLS certificates for prod cluster (variant 24) | Closed | Change Request | High | 2026-03-27 16:15 | 2026-05-01 16:15 | 2026-06-17 | Alice Martin | James Taylor | https://jira.example.com/browse/CR-1024 |  |  | 36 | TRUE | -45 | -45
CR-1025 | Add multi-region failover support (variant 25) | Open | Change Request | Medium | 2026-01-01 16:15 | 2026-04-21 16:15 | 2026-01-12 | Charlie Kumar | Olivia Brown | https://jira.example.com/browse/CR-1025 |  |  | 121 | TRUE | 111 | 110
CR-1026 | Consolidate microservice configs to Vault (variant 26) | Closed | Change Request | Medium | 2026-01-09 16:15 | 2026-05-01 16:15 | 2026-04-18 | Grace Kim | Olivia Brown | https://jira.example.com/browse/CR-1026 |  |  | 113 | TRUE | 15 | 15
CR-1027 | Implement rate limiting on public API (variant 27) | Under Review | Change Request | Medium | 2025-10-02 16:15 | 2026-03-19 16:15 | 2025-10-21 | Dana Fischer | James Taylor | https://jira.example.com/browse/CR-1027 |  |  | 212 | TRUE | 194 | 190
CR-1028 | Upgrade authentication module to OAuth2 (variant 28) | Approved | Change Request | Medium | 2025-05-19 16:15 | 2025-07-08 16:15 | 2025-08-16 | Grace Kim | James Taylor | https://jira.example.com/browse/CR-1028 |  |  | 348 | TRUE | 260 | 260
CR-1029 | Refactor payment gateway integration (variant 29) | Approved | Change Request | High | 2025-12-22 16:15 | 2026-04-15 16:15 | 2026-03-07 | Dana Fischer | Maria Lopez | https://jira.example.com/browse/CR-1029 |  |  | 131 | TRUE | 57 | 55
CR-1030 | Migrate database to PostgreSQL 16 (variant 30) | Open | Change Request | Medium | 2026-03-21 16:15 | 2026-04-25 16:15 | 2026-07-16 | Eve Santos | James Taylor | https://jira.example.com/browse/CR-1030 |  |  | 42 | TRUE | -74 | -75
CR-1031 | Refactor payment gateway integration (variant 31) | Approved | Change Request | Medium | 2026-03-12 16:15 | 2026-03-27 16:15 |  | Bob Chen | Olivia Brown | https://jira.example.com/browse/CR-1031 |  |  | 51 | FALSE
CR-1032 | Replace legacy logging with structured logs (variant 32) | Approved | Change Request | High | 2026-03-29 16:15 | 2026-04-22 16:15 | 2026-04-05 | Frank Muller | Paul Davis | https://jira.example.com/browse/CR-1032 |  |  | 34 | TRUE | 28 | 25
CR-1033 | Update TLS certificates for prod cluster (variant 33) | Under Review | Change Request | High | 2025-05-25 16:15 | 2025-08-12 16:15 |  | Alice Martin | Paul Davis | https://jira.example.com/browse/CR-1033 |  |  | 342 | FALSE
CR-1034 | Upgrade authentication module to OAuth2 (variant 34) | Closed | Change Request | Medium | 2025-07-25 16:15 | 2025-08-23 16:15 | 2025-09-10 | Grace Kim | Paul Davis | https://jira.example.com/browse/CR-1034 |  |  | 281 | TRUE | 235 | 235
CR-1035 | Patch CVE-2025-1234 in auth library (variant 35) | In Progress | Change Request | High | 2026-02-07 16:15 | 2026-02-17 16:15 | 2026-04-20 | Alice Martin | Maria Lopez | https://jira.example.com/browse/CR-1035 |  |  | 84 | TRUE | 13 | 10