## Sheet1
Key | Summary | Status | Issue Type | Priority | Created | Updated | Due Date | Assignee | Reporter | Link | Update_Due_Date | Meeting_Comments | Age_Days | Has_Due_Date | Lag_Days | Due_Deviation_Bucket
PR-2001 | Dashboard charts render blank on Firefox (case 1) | Closed | Problem Report | Medium | 2025-10-07 16:15 | 2026-03-01 16:15 | 2026-02-04 | Eve Santos | James Taylor | https://jira.example.com/browse/PR-2001 |  |  | 207 | TRUE | 88 | 85
PR-2002 | File upload fails for files > 50MB (case 2) | Root Cause Analysis | Problem Report | Low | 2025-09-29 16:15 | 2026-02-20 16:15 |  | Bob Chen | Nate Williams | https://jira.example.com/browse/PR-2002 |  |  | 215 | FALSE
PR-2003 | Timezone mismatch in scheduled reports (case 3) | Root Cause Analysis | Problem Report | Medium | 2025-12-30 16:15 | 2026-03-25 16:15 | 2026-01-22 | Grace Kim | James Taylor | https://jira.example.com/browse/PR-2003 |  |  | 123 | TRUE | 101 | 100
PR-2004 | Memory leak in notification service (case 4) | Closed | Problem Report | High | 2026-04-27 16:15 | 2026-04-27 16:15 | 2026-07-15 | Charlie Kumar | Maria Lopez | https://jira.example.com/browse/PR-2004 |  |  | 5 | TRUE | -73 | -75
PR-2005 | Search indexer crashes on Unicode input (case 5) | Root Cause Analysis | Problem Report | High | 2025-11-04 16:15 | 2026-01-05 16:15 |  | Grace Kim | Paul Davis | https://jira.example.com/browse/PR-2005 |  |  | 179 | FALSE
PR-2006 | Login fails intermittently on Safari (case 6) | Reopened | Problem Report | Medium | 2025-11-28 16:15 | 2026-04-12 16:15 |  | Charlie Kumar | James Taylor | https://jira.example.com/browse/PR-2006 |  |  | 155 | FALSE
PR-2007 | CSV export truncates rows beyond 10k (case 7) | Closed | Problem Report | High | 2026-02-22 16:15 | 2026-03-07 16:15 | 2026-06-22 | Charlie Kumar | Paul Davis | https://jira.example.com/browse/PR-2007 |  |  | 69 | TRUE | -50 | -50
PR-2008 | Timezone mismatch in scheduled reports (case 8) | Reopened | Problem Report | Low | 2026-01-14 16:15 | 2026-02-09 16:15 |  | Eve Santos | Olivia Brown | https://jira.example.com/browse/PR-2008 |  |  | 108 | FALSE
PR-2009 | Memory leak in notification service (case 9) | Reopened | Problem Report | High | 2025-12-24 16:15 | 2026-01-06 16:15 |  | Charlie Kumar | James Taylor | https://jira.example.com/browse/PR-2009 |  |  | 129 | FALSE
PR-2010 | API returns 500 on concurrent batch uploads (case 10) | Reopened | Problem Report | High | 2026-04-30 16:15 | 2026-05-02 16:15 | 2026-05-23 | Frank Muller | Olivia Brown | https://jira.example.com/browse/PR-2010 |  |  | 2 | TRUE | -20 | -20
PR-2011 | File upload fails for files > 50MB (case 11) | Open | Problem Report | Medium | 2025-07-18 16:15 | 2025-10-02 16:15 | 2025-08-03 | Eve Santos | Paul Davis | https://jira.example.com/browse/PR-2011 |  |  | 288 | TRUE | 273 | 270
PR-2012 | Search indexer crashes on Unicode input (case 12) | Open | Problem Report | Low | 2026-02-15 16:15 | 2026-03-26 16:15 | 2026-02-27 | Bob Chen | Maria Lopez | https://jira.example.com/browse/PR-2012 |  |  | 76 | TRUE | 65 | 65
PR-2013 | User session expires prematurely after MFA (case 13) | Reopened | Problem Report | High | 2026-03-10 16:15 | 2026-04-05 16:15 | 2026-05-27 | Bob Chen | Maria Lopez | https://jira.example.com/browse/PR-2013 |  |  | 53 | TRUE | -24 | -25
PR-2014 | API returns 500 on concurrent batch uploads (case 14) | Reopened | Problem Report | Low | 2026-01-31 16:15 | 2026-02-03 16:15 |  | Grace Kim | Olivia Brown | https://jira.example.com/browse/PR-2014 |  |  | 91 | FALSE
PR-2015 | Mobile app crashes on Android 14 cold start (case 15) | Open | Problem Report | Low | 2025-12-25 16:15 | 2026-01-21 16:15 | 2026-04-11 | Bob Chen | Maria Lopez | https://jira.example.com/browse/PR-2015 |  |  | 128 | TRUE | 22 | 20
PR-2016 | SSO redirect loop on Chrome incognito (case 16) | In Progress | Problem Report | High | 2025-09-08 16:15 | 2026-03-30 16:15 | 2025-12-29 | Frank Muller | Maria Lopez | https://jira.example.com/browse/PR-2016 |  |  | 236 | TRUE | 125 | 125
PR-2017 | Audit log missing entries for bulk operations (case 17) | Root Cause Analysis | Problem Report | High | 2025-10-09 16:15 | 2025-10-26 16:15 | 2026-02-03 | Eve Santos | Olivia Brown | https://jira.example.com/browse/PR-2017 |  |  | 205 | TRUE | 89 | 85
PR-2018 | Slow query on order history endpoint (>5s p99) (case 18) | Root Cause Analysis | Problem Report | High | 2025-07-31 16:15 | 2025-09-28 16:15 | 2025-08-10 | Charlie Kumar | James Taylor | https://jira.example.com/browse/PR-2018 |  |  | 275 | TRUE | 266 | 265
PR-2019 | Audit log missing entries for bulk operations (case 19) | Root Cause Analysis | Problem Report | High | 2026-03-07 16:15 | 2026-04-22 16:15 | 2026-04-27 | Eve Santos | James Taylor | https://jira.example.com/browse/PR-2019 |  |  | 56 | TRUE | 6 | 5
PR-2020 | Email notifications delayed by 30+ minutes (case 20) | Open | Problem Report | Medium | 2025-10-16 16:15 | 2025-12-03 16:15 |  | Alice Martin | Paul Davis | https://jira.example.com/browse/PR-2020 |  |  | 198 | FALSE
PR-2021 | Search indexer crashes on Unicode input (case 21) | Fix Deployed | Problem Report | Critical | 2025-07-30 16:15 | 2025-11-07 16:15 |  | Frank Muller | Nate Williams | https://jira.example.com/browse/PR-2021 |  |  | 276 | FALSE
PR-2022 | CSV export truncates rows beyond 10k (case 22) | Root Cause Analysis | Problem Report | Medium | 2025-11-22 16:15 | 2025-12-23 16:15 |  | Frank Muller | Olivia Brown | https://jira.example.com/browse/PR-2022 |  |  | 161 | FALSE
PR-2023 | API returns 500 on concurrent batch uploads (case 23) | In Progress | Problem Report | High | 2025-11-15 16:15 | 2026-04-05 16:15 | 2025-12-29 | Dana Fischer | Maria Lopez | https://jira.example.com/browse/PR-2023 |  |  | 168 | TRUE | 125 | 125
PR-2024 | Email notifications delayed by 30+ minutes (case 24) | Root Cause Analysis | Problem Report | High | 2025-07-14 16:15 | 2025-07-14 16:15 | 2025-09-29 | Grace Kim | Paul Davis | https://jira.example.com/browse/PR-2024 |  |  | 292 | TRUE | 216 | 215
PR-2025 | File upload fails for files > 50MB (case 25) | Fix Deployed | Problem Report | Medium | 2025-11-18 16:15 | 2026-01-11 16:15 | 2026-01-20 | Grace Kim | Maria Lopez | https://jira.example.com/browse/PR-2025 |  |  | 165 | TRUE | 103 | 100
PR-2026 | User session expires prematurely after MFA (case 26) | Root Cause Analysis | Problem Report | Critical | 2026-03-19 16:15 | 2026-04-28 16:15 | 2026-06-18 | Grace Kim | Maria Lopez | https://jira.example.com/browse/PR-2026 |  |  | 44 | TRUE | -46 | -50
PR-2027 | Login fails intermittently on Safari (case 27) | Open | Problem Report | High | 2025-11-24 16:15 | 2025-12-31 16:15 | 2025-12-26 | Dana Fischer | Paul Davis | https://jira.example.com/browse/PR-2027 |  |  | 159 | TRUE | 128 | 125
PR-2028 | Dashboard charts render blank on Firefox (case 28) | Reopened | Problem Report | Medium | 2026-03-25 16:15 | 2026-04-30 16:15 | 2026-07-23 | Dana Fischer | Olivia Brown | https://jira.example.com/browse/PR-2028 |  |  | 38 | TRUE | -81 | -85
PR-2029 | Slow query on order history endpoint (>5s p99) (case 29) | Open | Problem Report | Medium | 2025-12-28 16:15 | 2025-12-28 16:15 | 2026-04-02 | Bob Chen | Maria Lopez | https://jira.example.com/browse/PR-2029 |  |  | 125 | TRUE | 31 | 30
PR-2030 | Slow query on order history endpoint (>5s p99) (case 30) | Open | Problem Report | Medium | 2025-08-09 16:15 | 2025-12-14 16:15 | 2025-10-26 | Grace Kim | Olivia Brown | https://jira.example.com/browse/PR-2030 |  |  | 266 | TRUE | 189 | 185
PR-2031 | Audit log missing entries for bulk operations (case 31) | Fix Deployed | Problem Report | Medium | 2025-08-03 16:15 | 2026-01-12 16:15 |  | Frank Muller | Paul Davis | https://jira.example.com/browse/PR-2031 |  |  | 272 | FALSE
PR-2032 | Payment webhook retries cause duplicate charges (case 32) | In Progress | Problem Report | Medium | 2025-09-25 16:15 | 2026-02-12 16:15 |  | Dana Fischer | Olivia Brown | https://jira.example.com/browse/PR-2032 |  |  | 219 | FALSE
PR-2033 | Audit log missing entries for bulk operations (case 33) | Closed | Problem Report | Medium | 2025-12-20 16:15 | 2026-02-28 16:15 |  | Bob Chen | Nate Williams | https://jira.example.com/browse/PR-2033 |  |  | 133 | FALSE
PR-2034 | Email notifications delayed by 30+ minutes (case 34) | Root Cause Analysis | Problem Report | High | 2025-09-18 16:15 | 2025-11-17 16:15 | 2025-10-31 | Eve Santos | James Taylor | https://jira.example.com/browse/PR-2034 |  |  | 226 | TRUE | 184 | 180
PR-2035 | CSV export truncates rows beyond 10k (case 35) | In Progress | Problem Report | Critical | 2026-02-20 16:15 | 2026-03-11 16:15 | 2026-04-17 | Dana Fischer | Nate Williams | https://jira.example.com/browse/PR-2035 |  |  | 71 | TRUE | 16 | 15
PR-2036 | SSO redirect loop on Chrome incognito (case 36) | Fix Deployed | Problem Report | High | 2025-07-28 16:15 | 2025-11-10 16:15 | 2025-08-11 | Grace Kim | Paul Davis | https://jira.example.com/browse/PR-2036 |  |  | 278 | TRUE | 265 | 265
PR-2037 | User session expires prematurely after MFA (case 37) | Fix Deployed | Problem Report | Medium | 2026-04-21 16:15 | 2026-05-03 16:15 |  | Charlie Kumar | Nate Williams | https://jira.example.com/browse/PR-2037 |  |  | 11 | FALSE
PR-2038 | File upload fails for files > 50MB (case 38) | Reopened | Problem Report | Medium | 2025-10-14 16:15 | 2026-01-29 16:15 |  | Grace Kim | Paul Davis | https://jira.example.com/browse/PR-2038 |  |  | 200 | FALSE
PR-2039 | Payment webhook retries cause duplicate charges (case 39) | Open | Problem Report | High | 2026-01-09 16:15 | 2026-03-05 16:15 | 2026-02-19 | Frank Muller | Olivia Brown | https://jira.example.com/browse/PR-2039 |  |  | 113 | TRUE | 73 | 70
PR-2040 | User session expires prematurely after MFA (case 40) | Closed | Problem Report | Critical | 2026-02-06 16:15 | 2026-02-22 16:15 |  | Dana Fischer | Paul Davis | https://jira.example.com/browse/PR-2040 |  |  | 85 | FALSE
PR-2041 | Timezone mismatch in scheduled reports (case 41) | Fix Deployed | Problem Report | Critical | 2025-07-17 16:15 | 2025-08-28 16:15 |  | Dana Fischer | Maria Lopez | https://jira.example.com/browse/PR-2041 |  |  | 289 | FALSE
PR-2042 | Payment webhook retries cause duplicate charges (case 42) | Root Cause Analysis | Problem Report | High | 2026-04-06 16:15 | 2026-04-12 16:15 | 2026-05-24 | Dana Fischer | Nate Williams | https://jira.example.com/browse/PR-2042 |  |  | 26 | TRUE | -21 | -25
PR-2043 | Login fails intermittently on Safari (case 43) | Reopened | Problem Report | Medium | 2025-09-28 16:15 | 2026-01-26 16:15 | 2025-10-15 | Charlie Kumar | Maria Lopez | https://jira.example.com/browse/PR-2043 |  |  | 216 | TRUE | 200 | 200
PR-2044 | Audit log missing entries for bulk operations (case 44) | Open | Problem Report | Low | 2026-03-27 16:15 | 2026-03-29 16:15 |  | Bob Chen | James Taylor | https://jira.example.com/browse/PR-2044 |  |  | 36 | FALSE
PR-2045 | User session expires prematurely after MFA (case 45) | In Progress | Problem Report | Medium | 2026-02-12 16:15 | 2026-02-26 16:15 | 2026-04-20 | Charlie Kumar | Nate Williams | https://jira.example.com/browse/PR-2045 |  |  | 79 | TRUE | 13 | 10